## Sheet1
Gangles Ice Stupa 2020-21 season timeline
Date | Activity | Questions
2020-12-26 | Dome 1 making start
2020-12-27 | Dome 1 making finish, started water at 3 PM
2020-12-28
2020-12-29 | Water frozen around 5 AM, pipe cleared and started water at 4 PM
2020-12-30 | Water frozen around 5 AM, pipe cleared and started water at 4 PM
2020-12-31 | Water frozen around 5 AM, pipe cleared and started water at 4:30 PM
2021-01-01
2021-01-02
2021-01-03 | Water frozen around 5 AM and pipe clearing in progress
2021-01-04 | Started water at 5 PM
2021-01-05 | Water frozen, pipe cleared and started water at 4:30 PM
2021-01-06
2021-01-07 | Water frozen, pipe cleared and started water at 4:30 PM
2021-01-08
2021-01-09 | Water frozen, pipe cleared, added umbu and started water at 4:30 PM
2021-01-10
2021-01-11
2021-01-12 | Water frozen, pipe cleared, added umbu and started water at 5 PM
2021-01-13
2021-01-14
2021-01-15 | Water frozen, pipe cleared, started making dome 2 and started water at 4 PM
2021-01-16
2021-01-17
2021-01-18 | Water frozen, pipe cleared, dome 2 completed, started water via dome 2 at 4.30 PM through vaccume pipe | Fountain height: 5 m?(2 GI pipes of 6 ft)
2021-01-19 | Water running, dome 2 collapsed & remade by added umbu and started water at 4.30 PM
2021-01-20
2021-01-21 | Water frozen, pipe cleared, started making dome 2 and started water at 5:30 PM
2021-01-22 | Water running, added GI pipe & umbu and started water at 5 PM | Fountain height: 9 m? (4 GI pipes of 6 ft)
2021-01-23 | Water running, added umbu and started water at 5 PM
2021-01-24 | Water running, added umbu and started water at 5 PM
2021-01-25
2021-01-26
2021-01-27
2021-01-28
2021-01-29 | Water head frozen, redid the channel and partially cleared ice
2021-01-30 | Water head frozen, redid the channel and partially cleared ice
2021-01-31 | Completed clearing the ice within channel and started water at 5 PM
2021-02-01
2021-02-02 | Water frozen, pipe cleared and started water at 5:30 PM
2021-02-03
2021-02-04
2021-02-05
2021-02-06
2021-02-07 | Pipe slipped from source and hence frozen, pipe cleared and started water at 6 PM
2021-02-08
2021-02-09 | Water frozen, pipe cleared and started water at 5:30 PM
2021-02-10
2021-02-11
2021-02-12
2021-02-13 | Water frozen, pipe cleared, added umbu & threads and started water at 5:30 PM
2021-02-14 | Water running, added umbu & threads and started water at 4 PM
2021-02-15 | Water running, added umbu & threads and started water at 4 PM
2021-02-16
2021-02-17
2021-02-18
2021-02-19 | Water frozen, pipe cleared and started water at 5:30 PM
2021-02-20
2021-02-21
2021-02-22 | Pipe slipped from source and hence frozen, pipe cleared and started water at 4 PM
2021-02-23
2021-02-24 | Water running, added umbu & threads and started water at 4 PM
2021-02-25
2021-02-26
2021-02-27 | Water running, added umbu & threads and started water at 4 PM
2021-02-28
2021-03-01
2021-03-02
2021-03-03 | Geophysical data measurement at Gangles, water started at 5 PM
2021-03-04
2021-03-05 | Water running, added umbu & threads and started water at 5 PM
2021-03-06 | Pipe slipped from source and hence frozen, pipe cleared and started water at 4 PM
2021-03-07 | Water frozen, pipe cleared, added umbu & threads and started water at 5:30 PM
2021-03-08 | Water frozen, pipe cleared and started water at 5:30 PM
2021-03-09 | Water frozen, pipe cleared and started water at 5:30 PM
2021-03-10 | Pipe frozen and last day for Gangles IS (didn’t sprinkle water further)